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February 15, 2018

Mrs. Judith Whitney, Clerk

Vermont Public Utility Commission

112 State Street

Drawer 20

Montpelier, VT 05620

Re:
Petition of Chelsea Solar LLC, pursuant to 30 V.S.A. § 248, for a certificate of public good authorizing the installation and operation of the “Chelsea Solar Project,” a 2.0 MW solar electric generation facility located on Willow Road in Bennington, Vermont (PUC Case # 17-5024-PET)

Dear Mrs. Whitney:

In accordance with the order of February 14, 2018, on behalf of Chelsea Solar LLC (“Chelsea Solar”), I have enclosed the Petitioner’s proposed schedule.  While the proposed schedule may seem accelerated, there are two important points to consider.  First, every party to this proceeding has reviewed this project and the neighboring Apple Hill project at least three times already. Thus the parties already have in their possession through the prior Chelsea Solar docket, and docket 8454, all information that is relevant. Second, a schedule is needed that will allow sufficient time to order equipment, to ensure sufficient time to order equipment, build the project, commission the project and complete the interconnection.  Taking into account the fact that the weather might impair progress from November, we really need a schedule that has a CPG issued on or around May 25, 2018, in order to achieve a commission date of December 4, 2018, which date assumes the PUC grants the extension request that is currently before it.

Sincerely,

/s/ Michael Melone

Michael Melone

Allco Renewable Energy Limited

1745 Broadway, 17th Floor

New York, NY 10019

Attorneys for Chelsea Solar LLC
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