## Master Schedule
Date Range |  |  |  |  | Location(s)
From | To | Intended Work / Milestones | ARC Team Remote | ARC Team in VT | Calgary | BED | DPS
2026-06-08 | 2026-06-10 | Final collection of information / interviews | Darwin, others as needed | Lothar | P | P
2026-06-11 | 2026-06-12 | Final collection of information / interviews | others as needed | Lothar, Darwin, Dave | P | P
2026-06-15 | 2026-06-23 | Prep for draft observations | All |  | P
2026-06-24 | 2026-06-24 | BED draft observations review meeting (2 hrs) (on site + Teams) | All others | Lothar, Darwin | P | P
2026-06-25 | 2026-06-25 | DPS draft observations review meeting (2 hrs) (on site?? + Teams) | All others | Lothar, Darwin | P |  | P
2026-06-26 | 2026-06-26 | DPS and BED final questions | All others | Lothar, Darwin | P | P | P
2026-06-27 | 2026-07-07 | Prep draft deliverable (or contingency) | All |  | P
2026-07-08 | 2026-07-08 | Present draft deliverable to BED (2 hrs) | others as needed | Lothar, Darwin | P | P
2026-07-08 | 2026-07-09 | BED - 2 day gap for for technical review & questions, additional items for research or response | others as needed | Lothar, Darwin | P | P
2026-07-10 | 2026-07-10 | Present draft deliverable to DPS (2 hrs) (on-site or via Teams or hybrid) | others as needed | Lothar, Darwin | P |  | P
2026-07-13 | 2026-07-16 | DPS revisions and follow up (on-site or via Teams or hybrid) | others as needed | Lothar, Darwin | P |  | P
2026-07-20 | 2026-07-20 | review DPS revisions with BED deliver final draft | others as needed | Lothar, Darwin | P | P
2026-07-20 | 2026-07-22 | BED - 3 day gap for response / confirmation of understanding DPS revisions | others as needed | Lothar, Darwin | P | P
2026-07-23 | 2026-07-23 | Present final document to DPS | others as needed | Lothar, Darwin | P |  | P
2026-07-24 | 2026-07-31 | <contingency> | others as needed | Lothar, Darwin | P | P | P